## IA
Investment Analysis | [6 empty] | Date Created |  | Created By: | Final HUD -1 Purchase | Closing Date: |  | Final HUD-1 Resale | Closing Date: |  | Net Profits (FINAL - Checks Cut) |  |  |  | Legend
Address: | 15620 Ramona Rd , Apple Valley , CA 92307 |  | Estimated Project in Mos. | 7.4667 |  |  | Estimated Prelim |  | Hard Money - Anchor | Total Consideration | 0 | 0 |  | Debits | Credits |  | HomeStrongUSA | Developer Partner | Fund Control
| TOTAL PURCHASE COST | [5 empty] | Net Purchase Price |  | Gray = data input | Adjustments to Purchase Price | 0 | 0 | Purchase Price | 0 | 0 | ROI Adjustment | 0 |  |  |  |  | Utilities | Financing Type | Yes | NA
65.22% | 300000 | Purchase Price | 320218.25 |  | 2025-11-07 | COE Date | Opening Bid Amount |  | 65000 | Tax Proration's (County & Suptl) | 0 | 0 | Per Diem Adjustment | 0 | 0 |  |  |  |  | Estimated Prelim | Estimated Repairs | Rehab | Hard Money - Anchor | No | Alex Soto
2.826% | 13000 | Due Diligence Cost | 456618.02 |  | 2026-06-19 | EOM | ROI Adjustment to Purchase Price | 0% | 0 | Deposits in Escrow |  |  | Payoff 1 | 0 | 0 |  |  |  |  | Acquisition Approved | Preliminary Bid | Change Order | Hard Money - DP |  | Pfaff
0.6528% | 3003 | Insurance | 136399.77 | Refund | 224 |  |  |  | 65000 |  | 0 | 0 | Principle | 0 | 0 |  |  |  |  | Final HUD -1 Purchase | Per Bid | HOA | Hard Money |  | Ron Gutierrez
0% | 0 | Cash for Keys |  |  |  |  | HomeStrong USA Fees |  | Gray = data input |  | 0 | 0 | Interest | 0 | 0 | Escrow Refund | 0 |  |  | Estimated HUD-1 Resale | Final Repair Cost | 1st Loan Payments | Donation |  | Sanner
0.5455% | 2509.25 | Escrow and Title |  |  |  |  | Include Fees in Escrow? |  | Yes |  | 0 | 0 | Loan Fees 1st | 0 | 0 | Total Deposits | 0 | 0 | 0 | Final HUD-1 Resale |  | 2nd Loan Payments | Donation - Refi |  | HD
0% |  | Prorated Property Tax |  | Total Cash Investmetn Including Payments | 79901.9808 |  | Is the Property Occupied? |  | 5000 |  | 0 | 0 | Statement Fee | 0 | 0 | [6 empty] | Lender Fees | Cash Purchase |  | HSUSA
69.24% | 318512.25 | Total Purchase Costs |  | Cash Required to Close: | 49747.9253 |  |  |  |  | New Loans |  |  | Reconveyance Fee | 0 | 0 | Total Repairs | 0 | 0 |  |  |  | Misc.
| LENDER COST | [6 empty] | Auction Fee |  | New Loan to File 1st | 0 | 0 | Demand Fee | 0 | 0 |  |  |  |  | Cost Breakdown
1st LOAN | [8 empty] | 5000 | New Loan to File 2nd | 0 | 0 | Payment to Lender | 0 | 0 |  |  |  |  | Utilities | 0
0% |  | Prepaid Interest 1st | 10.45% | Interest Rate | 1st Loan Amount | Override Loan Am. | Due Diligence Fee |  | Gray = data input | Loan Origination Fees | 0 |  | Unused Payment Credit | 0 | 0 |  |  |  |  | Rehab | 0
5.244% | 24123.2444 | Interest on New Loan 1st | 224 | Days | 371000 |  | Include Fees in Escrow? |  | No | Loan Origination Fee 1st (Combo) | 0 | 0 | Miscellaneous Loan Fees | 0 | 0 |  |  |  |  | Change Order | 0
0.8065% | 3710 | Loan Origination Fee 1st | 1% | Points | 345000 | 75% of ARV | Certified Inspection Fee |  | 0 | Loan Origination Fee 2nd | 0 | 0 | Loan Draw Balance | 0 | 0 |  |  |  |  | HOA | 0
0.2172% | 999 | Loan Fees & Appraisal Fee 1st | 999 | Est. Loan Fees | 270000 | 90% of Cost | Appraisal Fee |  | 0 | Loan Fees 1st (Combo) | 0 |  | Payoff 2 | 0 | 0 |  |  |  |  | 1st Loan Payments | 0
0% |  |  |  | Appraisal Fee | 3230.7917 | Mo.Payment | Permit Search Fee |  | 0 | Processing Fee | 0 | 0 | Principle | 0 | 0 |  |  |  |  | 2nd Loan Payments | 0
0% |  |  | 24454.08 |  | 224 | odd days | Budget and SOW Fee |  | 0 | Admin Fee | 0 | 0 | Interest | 0 | 0 |  |  |  |  | Lender Fees | 0
0% |  |  |  |  | 31 | Day in Mo | Contingency |  | 0 | Underwriting Fee | 0 | 0 | Loan Fees 2nd | 0 | 0 |  |  |  |  | Misc. | 0
[5 empty] | 23345.0753 | ProRated Payment
[5 empty] | 268764.3247 | ShortFunds to Escrow | Due Diligence Fee |  | 0 | Loan Document Fee | 0 | 0 | Other Fees | 0 | 0 |  |  |  |  | Supplemental Tax Estimator
2nd LOAN
0% |  |  | 12% | Interest Rate |  |  | Loans |  | Gray = data input | Wire Fee | 0 | 0 | Unused Payment Credit | 0 | 0 |  |  |  |  | Tax Factor
0% |  | Interest from 2nd Payoff | 224 | Days | 2nd Loan Amount |  | Final Sales Price |  | Loan | Tax Service | 0 | 0 | Sales Commission | 0 | 0 |  |  |  |  | 6 | June | 1
0% |  |  | 0% | Points |  |  | 460000 | 65% | 299000 | Flood Cert | 0 | 0 | Buyers Agent Commissions | 0 | 0 |  |  |  |  | 7 | July | 0.9167
0% | 0 | Loan Fees 2nd | 0 | Est. Loan Fees |  |  | Opening Bid Amount |  | (which ever is less) | Notary | 0 | 0 | Listing Agents Commissions | 0 | 0 |  |  |  |  | 8 | August | 0.8333
0% | 0 | Additional 2nd Payments Made |  |  |  |  | 65000 | 80% | 52000 | Appraisal Fee | 0 | 0 | Tax Proration's | 0 | 0 |  |  |  |  | 9 | September | 0.75
0% | 0 | Unused 2nd Payments Credit |  |  |  |  | Payment Reserves 1st | 0 | 0 | Inspection Fee | 0 | 0 | County Taxes | 0 | 0 |  |  |  |  | 10 | October | 0.667
0% | 0 | Interest from 2nd Payoff |  |  |  |  | Payment Reserves 2nd | 0 | 0 | Loan Fees 2nd | 0 |  | 1st Half Taxes | 0 | 0 |  |  |  |  | 11 | November | 0.583
6.268% | 28832.2444 | Total Lender Costs |  |  |  |  | Estimated Construction Hold Back |  | 0 | Processing Fee | 0 | 0 | 2nd Half Taxes | 0 | 0 |  |  |  |  | 12 | December | 0.5
| REHABILITATION COSTS | [5 empty] | Loan Amount |  | 318512.25 | Admin Fee | 0 | 0 | Escrow Charges | 0 | 0 |  |  |  |  | 1 | January | 0.417
16.13% | 74181.6 | Estimated Repairs |  |  |  |  | Estimated 2nd Loan Amount |  | 0 | Underwriting Fee | 0 | 0 | Settlement or Closing Fee | 0 | 0 |  |  |  |  | 2 | February | 0.3333
0% | 0 | Utilities |  |  |  |  | Supplemental Taxes |  | Gray = data input | Loan Document Fee | 0 | 0 | Payoff/Debt Processing | 0 | 0 |  |  |  |  | 3 | March | 0.25
16.13% | 74181.6 | Total Rehab Costs |  |  |  |  | Final Sales Price |  | 460000 | Prepaid Interest 1st | 0 |  | Wire Fee | 0 | 0 |  |  |  |  | 4 | April | 0.1667
| MISC COSTS | [5 empty] | Opening Bid Amount |  | 65000 | Months Prepaid Interest | 0 | 0 | Sub Escrow Fee | 0 | 0 |  |  |  |  | 5 | May | 0.0866
0% | 0 | ROI Adjustments |  |  |  |  | Tax Assessed Value |  |  | Interest on New Loan | 0 | 0 | Document Preparation | 0 | 0 |  |  |  |  | Supplemental Tax Bill #1 | 0
0% |  | Miscellaneous Costs |  |  |  |  | Increased Value |  | 395000 | Prepaid Interest 2nd | 0 |  | Miscellaneous Escrow Fees | 0 | 0 |  |  |  |  | Supplemental Tax Bill #2 | 0 |  | Interest Difference
0% | 0 | Supplemental Taxes |  |  |  |  | Total Capital Investment |  |  | Months Prepaid Interest | 0 | 0 | Title Charges | 0 | 0 | [7 empty] | 0
0% |  | Utilities | Monthly HOA Fee |  |  |  | Purchase Price |  | 300000 | Interest on New Loan | 0 | 0 | Owners Coverage | 0 | 0 |  |  |  |  | 1st Loan Interest Calculator
0% | 0 | HOA | 0 |  |  |  | Loan |  | -318512.25 | Construction Hold Back | 0 |  | Recording Fees | 0 | 0 |  |  |  |  | Amount of Loan | Interest Per Day | Days of Loan | Interest Due
0% | 0 | Additional Interest Reserve 1st | 0 | months |  |  | 2nd Loan or Rehab Float Amount |  | 0 |  | 0 | 0 | County Transfer Tax | 0 | 0 |  |  |  |  | 0 | 0 | 46202 | 0
0% | 0 | Additional Interest Reserve 2nd | 0 | months |  |  | Loan Fees & Cost |  | 4709 | Escrow & Title Fees | 0 | 0 | Miscellaneous Title Fees | 0 | 0
0% | 0 | Total Misc. Costs |  |  |  |  | Prorated Closing Interest |  | 24123.2444 | Escrow Fee | 0 | 0 | Additional Settlement Fees | 0 | 0 | [7 empty] | Interest Difference
GROSS PROFITS | [6 empty] | Construction Holdback |  | 0 | Lender Endorsement | 0 | 0 | Home Warranty | 0 | 0 | [7 empty] | 0
100% | 460000 | After Repair Value | Estimated Sales Price | 515000 |  |  | Payment Reserves | 0 Months |  | CLTA Interim Binder Form(Owners) | 0 | 0 | Property Disclosure Report | 0 | 0 |  |  |  |  | 2nd Loan Interest Calculator
0.5% | 2500 | Escrow and Title |  | Total Development Cost |  |  | Interest On 2nd/Rehab Float Int. | 0 Months |  | ALTA Ext Loan Policy 1st | 0 | 0 | HOA Fees | 0 | 0 |  |  |  |  | Amount of Loan | Interest Per Day | Days of Loan | Interest Due
0% | 1200 | Prorated Property Tax | 69.24% | 318512.25 | Total Acquisition Cost |  | Action Fee |  | 5000 | ALTA Ext Loan Policy 2nd | 0 | 0 | Transfer Fee | 0 | 0 |  |  |  |  | 0 | 0 | 46202 | 0
0% | 10000 | Concessions (Buyer's Help) | 6.268% | 28832.2444 | Hard Money Costs |  | Due Diligence Fee |  | 0 | Record 1st Trust Deed | 0 | 0 | HOA Dues | 0 | 0
2% | 9200 | Buyers Agent Commissions | 16.13% | 74181.6 | Rehab Costs |  | General Liability Insurance |  | 0 | Record 2nd Trust Deed | 0 | 0 | Seller Credits | 0 | 0
0% | 0 |  | 0% | 0 | Miscellaneous Costs Less Interest |  | Escrow & Title |  | 2509.25 | Record Deed Title | 0 | 0 | Seller Credit to Buyer | 0 | 0 |  |  |  |  | Loan Fees Calculator
0% | 645 |  | 91.64% | 421526.0944 | Total Development Cost |  | Funds To Close |  | 17829.2444 | Natural Hazard Report | 0 | 0 | Seller Credit Transfer Tax | 0 | 0 |  |  |  |  | Amount of Loan | Points | Lender Fees
0% | 299.95 | [5 empty] | Interest Reserve | 0 Months | 0 | HOA Fees | 0 | 0 | Seller Credit Owner's Policy | 0 | 0 |  |  |  |  | 0 | 1% | 0
94.82% | 436155.05 | Gross Profit to Seller |  |  |  |  | Interest On 2nd/Rehab Float Int. | 0 Months | 0 | Association Dues | 0 | 0 | Seller Credit Title and Escrow Fees | 0 | 0
| NET PROFITS | [5 empty] | Construction Holdback |  | 74181.6 | Professional Community Mgmt. | 0 | 0 | Pest Inspections and Repairs | 0 | 0
3.18% | 14628.9556 | Net Profit | Notes: |  |  | 65155.05 | HomeStrong USA |  | 0 | Post Closing Fee | 0 | 0 | Repairs Paid In Escrow | 0 | 0
| 11.07% | ROI |  |  |  | 119397.15 | Due Diligence Fee |  | 0 | Disbursements Paid |  |  | Miscellaneous Fees | 0 | 0
| 17.79% | IRR |  |  |  | -54242.1 | Misc.& Pad |  | 0 | Homeowners Insurance | 0 | 0 |  | 0 | 0
| 7314.4778 | [5 empty] | Total Reserves |  | 74181.6 | Community Dev. Fee | 0 | 0 |  | 0 | 0
[7 empty] | Total Out of Pocket Cash |  | 92010.8444 | Cash ( From)(X TO) Borrower | 0 | 0 |  | 0 | 0
|  |  | Approved By: |  | Date | [7 empty] | Payoffs
[14 empty] | #REF! | #REF!
|  |  | Resale |  |  | Purchase | [8 empty] | #REF! | Adjustments | 0 | 0
|  | Acquisition |  | 323632.95
|  | Rehab Materials |  | 23798.09
|  | Rehab Other |  | 20223.51
|  | Rehab Labor |  | 30150
|  | Holding |  | 23443.67
|  | Interest Charges |  | 2838.97
|  | Addtl Kiavi |  | 1938.48
|  | Settlement Charges |  | 24607.15
|  | Total |  | 450632.82
|  | Sales Price |  | 460000
|  | Profit |  | 9367.18
|  | Holdback |  | $ -
|  | Amount to be Disb |  | 9367.18

## Material & Labor
42820 | 10300 | 32520
Trade | Sub | Material | Unit | Unit Cost
Appliances |  | 1500
Windows |  | 0 | 7 | 250
Floring |  | 3520 | 2200 | 1.6
Kitchen & Vanaites |  | 7500
Tops Quartz |  |  | Part of kit bid |  |  | Acquisition |  | 422665.05
Front Siding |  | 0 |  |  |  | Rehab |  | 45318.77
General Material |  | 20000 |  |  |  | Rehab Labor |  | 26894.24
Plumbing Finishes | [5 empty] | Holding |  | 12489.95
Tile |  |  |  | 3.1 |  | Settlement Charges |  | 27880.12 | Per Estimated Closing Statement
Fraiming
Paint Flat in |  |  | 6 | 200 |  | Total |  | 535248.13
Rough Electrical
Drywall
Rough Plumbing
Finish Electrical
Paint saten out |  |  | 6 | 200
Roof
Landscape | 5000
HVAC | 2500
Vins | 2800
Sub | 10300
Material | 32520
Labor | 24000
Total | 66820
35050.35 | 9224.04 | 25826.31
Trade | Sub | Material | Unit | Unit Cost
Appliances |  | 1500
Windows |  | 0 | 7 | 250
Floring |  | 3300 | 2200 | 1.5
Kitchen & Vanaites |  | 5516.29
Tops Quartz |  |  | Part of kit bid
Front Siding |  | 0
General Material |  | 15510.02
Plumbing Finishes
Tile |  |  |  | 3.1
Fraiming
Paint Flat in |  |  | 6 | 200
Rough Electrical
Drywall
Rough Plumbing
Finish Electrical
Paint saten out |  |  | 6 | 200
Roof | 0
Landscape | 4000
HVAC | 2500
Vins | 2724.04
Sub | 9224.04
Material | 25826.31
Labor | 30000
Total | 65050.35
Type | Date | Num | Name | Memo | Amount | Rehab | Materials
Credit Card Charge | 2025-01-22 |  | A-G Sod Farms - Perris |  | 1097.33 | Rehab | Materials
Check | 2025-01-07 | 107 | Alec Ferreira |  | 200 | Rehab | Materials
Check | 2025-03-03 | WIRE | Anguiano Armenta Construction |  | 600 | Rehab | Labor
Check | 2025-02-26 | WIRE | Anguiano Armenta Construction |  | 969.92 | Rehab | Labor
Check | 2025-01-22 | Wire | Anguiano Armenta Construction |  | 2764.34 | Rehab | Labor
Check | 2024-12-20 | WIRE | Anguiano Armenta Construction |  | 5000 | Rehab | Labor
Check | 2025-01-06 | WIRE | Anguiano Armenta Construction |  | 5000 | Rehab | Labor |  |  | Row Labels | Sum of Amount
Check | 2024-12-27 | WIRE | Anguiano Armenta Construction |  | 6000 | Rehab | Labor |  |  | A-G Sod Farms - Perris | 1097.33 | Landscaping
Check | 2025-01-10 | WIRE | Anguiano Armenta Construction |  | 6000 | Rehab | Labor |  |  | Alec Ferreira | 200
Credit Card Credit | 2025-01-11 | 637 | Home Depot |  | -151.71 | Rehab | Materials |  |  | Anguiano Armenta Construction | 26334.26 | Labor
Credit Card Credit | 2025-01-17 | 639 | Home Depot |  | -88.19 | Rehab | Materials |  |  | Home Depot | 15510.02 | Material
Credit Card Credit | 2025-01-20 |  | Home Depot |  | -27.5 | Rehab | Materials |  |  | Jose Rodriguez | 650
Credit Card Credit | 2025-01-13 | 635 | Home Depot |  | -9.08 | Rehab | Materials |  |  | Juan Carlos Rodriguez | 11000 | Roof
Credit Card Charge | 2025-01-04 | 686 | Home Depot |  | 72.86 | Rehab | Materials |  |  | LIST TO SOLD MEDIA | 575
Credit Card Charge | 2025-01-13 | 660 | Home Depot |  | 100.27 | Rehab | Materials |  |  | Ovier Landscaping | 2576 | Landscapin
Credit Card Charge | 2025-01-15 | 654 | Home Depot |  | 122.76 | Rehab | Materials |  |  | SHERWIN-WILLIAMS701614 | 436.05 | Material
Credit Card Charge | 2025-01-22 |  | Home Depot |  | 122.86 | Rehab | Materials |  |  | The Elite Group | 449
Credit Card Charge | 2025-01-04 | 687 | Home Depot |  | 129.86 | Rehab | Materials |  |  | WM.COM | 2724.04 | Trash
Credit Card Charge | 2025-01-25 |  | Home Depot |  | 137.71 | Rehab | Materials |  |  | WPY*ROSA E ESCOBAR | 4689.3 | Window
Credit Card Charge | 2025-02-21 |  | Home Depot |  | 138.17 | Rehab | Materials |  |  | Z H STONE GROUP, INC. | 5516.29 | Kitchen
Credit Card Charge | 2025-01-08 | 676 | Home Depot |  | 158.64 | Rehab | Materials |  |  | (blank)
Credit Card Charge | 2025-02-21 |  | Home Depot |  | 339.07 | Rehab | Materials |  |  | Grand Total | 71757.29
Credit Card Charge | 2025-01-25 |  | Home Depot |  | 583.75 | Rehab | Materials
Credit Card Charge | 2025-02-04 | 703 | Home Depot |  | 707.8 | Rehab | Materials
Credit Card Charge | 2025-01-18 | 696 | Home Depot |  | 764.03 | Rehab | Materials
Credit Card Charge | 2025-01-09 | 670 | Home Depot |  | 999.28 | Rehab | Materials
Credit Card Charge | 2025-01-11 | 663 | Home Depot |  | 1196.85 | Rehab | Materials
Credit Card Charge | 2024-12-28 | 610 | Home Depot |  | 1215.33 | Rehab | Materials
Credit Card Charge | 2025-01-18 | 691 | Home Depot |  | 1378.49 | Rehab | Materials
Credit Card Charge | 2025-01-15 | 655 | Home Depot |  | 1559.14 | Rehab | Materials
Credit Card Charge | 2024-12-23 | 617 | Home Depot |  | 1571.86 | Rehab | Materials
Credit Card Charge | 2024-12-23 | 614 | Home Depot |  | 1600.9 | Rehab | Materials
Credit Card Charge | 2025-01-17 | 643 | Home Depot |  | 2886.87 | Rehab | Materials
Check | 2025-03-03 |  | Jose Rodriguez |  | 650 | Rehab | Materials
Check | 2024-12-22 | 105 | Juan Carlos Rodriguez | Roof Final | 4000 | Rehab | Materials
Check | 2024-12-19 | WIRE | Juan Carlos Rodriguez | Roof | 7000 | Rehab | Materials
Credit Card Charge | 2025-01-29 | 711 | LIST TO SOLD MEDIA |  | 575 | Holding
General Journal | 2025-01-28 | 182 | Ovier Landscaping |  | 1176 | Rehab | Materials
General Journal | 2025-01-22 | 176 | Ovier Landscaping |  | 1000 | Rehab | Materials
General Journal | 2025-02-20 | 181 | Ovier Landscaping |  | 400 | Rehab | Materials
Credit Card Charge | 2025-01-17 | 645 | SHERWIN-WILLIAMS701614 |  | 436.05 | Rehab | Materials
Check | 2025-01-24 | ACH | The Elite Group |  | 449 | Holding
Credit Card Charge | 2025-02-20 |  | WM.COM |  | 100.96 | Holding
Credit Card Charge | 2025-01-11 | 665 | WM.COM |  | 103.48 | Holding
Credit Card Charge | 2024-12-20 | 624 | WM.COM |  | 523.25 | Rehab | Materials
Credit Card Charge | 2024-12-17 |  | WM.COM | Dumpster | 657.87 | Holding
Credit Card Charge | 2025-01-23 |  | WM.COM |  | 657.87 | Holding
Credit Card Charge | 2025-01-11 | 666 | WM.COM |  | 680.61 | Rehab | Materials
Credit Card Charge | 2024-12-21 | 619 | WPY*ROSA E ESCOBAR |  | 4689.3 | Rehab | Materials
Credit Card Charge | 2025-01-18 | 698 | Z H STONE GROUP, INC. |  | 135.32 | Rehab | Materials
Credit Card Charge | 2025-01-10 | 669 | Z H STONE GROUP, INC. |  | 5380.97 | Rehab | Materials

## SOW
EXTERIOR – FRONT | SOW Vidoe | https://www.youtube.com/watch?v=M7SDmi5ZSLA
Location | Item | Work Description | Timestamp
Front Fence | Fence | Verify structural stability; no repairs needed | 0:02
Driveway Left | Landscape – Pines | Keep two small pine trees; no action | 0:09
Driveway Left | Landscape | Scrape soil, remove debris, convert to clean dirt area | 0:17
Driveway Right | Large Pine Area | Organize and redistribute rocks around tree for cleaner layout | 0:24
Driveway Right | Rock Border | Remove loose rocks, reposition evenly, clean grade | 0:31
Front Yard | Landscape | Full scrape of soil areas; maintain dirt-only grading | 0:55
Front Yard | Fountain | Remove fountain completely; haul away | 1:08
Front Elevation | Exterior Lights | Replace all exterior lights with new fixtures | 1:19
Front Elevation | Brick Planter | Repair loose bricks, re-mortar, level top course | 1:23
Front Elevation | Exterior Paint | Paint full house exterior (stucco + fascia) | 1:30
Front Elevation | Fascia | Scrape chipped paint, prep, prime, and repaint | 2:11
Front Elevation | Windows | Keep all windows; clean thoroughly inside/out | 1:32 + 13:31
Front Elevation | Entry Lights | Replace entry light fixtures | approx 1:35
Front Elevation | Stucco | Patch stucco around hose bib, texture-match, paint | 1:48
Front Elevation | Garage Door | Replace entire garage door with new standard panel door | 1:58
Front Yard | Debris | Remove all yard debris, trash, loose material | 2:03
Front Door | Door + Hardware | Keep front door; paint and install new hardware | Supplemental Clip
🟦 EXTERIOR – BACK
Location | Item | Work Description | Timestamp
Right Side Yard | General Cleanup | Remove all trash, debris; full scrape | 3:06
Rear Yard | Patio Area | Remove loose items, scrape, clean | 3:20
Rear Yard | Holes in Ground | Fill holes; compact soil | 3:30
Rear Yard | Major Trash | Remove multiple piles, including old roofing materials | 5:25
Rear Yard | Burned Structure | KEEP structure, minimal repair + paint per your instruction | 4:02 clarification
Rear Yard | Wood Debris | Remove all unsafe or rotted wood around structure | 4:30
Rear Yard | Trash Piles | Large refuse removal; full yard cleanout | 5:00–5:20
Garage Exterior | Door (Rear) | Inspect and repair if needed; ensure secure close | 5:39
HVAC | Exterior Unit | Inspect operational condition | 9:38
Safe | Junk | Remove large safe from property | 16:24
🟦 GARAGE
Location | Item | Description | Timestamp
Garage | General | Keep popcorn ceiling; no ceiling work | 12:57
Garage | Water Heater | Leave in place; operational | 5:49 + 13:02
Garage | Cleanup | Basic cleaning only | 12:52
🟦 ENTRY
Location | Item | Description | Timestamp
Entry Wall | Wall Removal | Remove small wall and connected post | 6:22
Entry | Flooring | Install waterproof laminate ($1.49/sf) | Flooring Directive
🟦 LIVING ROOM / MAIN AREA
Location | Item | Description | Timestamp
Living Area | Ceiling | Remove popcorn ceilings | 6:36
Living Area | Fan | Replace ceiling fan | 6:32
Living Area | Accent Beams | Paint beam black or white (final TBD) | 6:47
Living Area | Fireplace | Paint fireplace black both sides | 10:13
Living Area | Cabinet | Remove cabinet near chimney | 10:07
Living + Kitchen | Wall Removal | Remove wall between kitchen and bar | 10:29–10:52
Living | Flooring | Install waterproof laminate ($1.49 sf) | 9:49
🟦 MASTER BEDROOM
Location | Item | Description | Timestamp
Master | Leak Damage | Inspect fresh roof leak, repair roof, repair ceiling | 7:20
Master | Wall Paneling | Keep all wall finishes | 7:35 (clarified)
Master Bath | Tub | Reglaze tub | 7:40
Master Bath | Toilet | Keep | 7:44
Master Bath | Vanity | New cabinet + faucet | 7:48
Master Bath | Vent | Replace vent fan | 7:52
Master | Doors | Keep door slabs; paint them | 7:59
Master | Closet Doors | Keep & paint | 8:03
Master | Hardware | Replace with new hardware | 8:25
Master | Flooring | Carpet | Flooring Directive
🟦 BATHROOMS (ALL)
Location | Item | Description | Timestamp
Hall Bath 1 | Toilet | Keep | 8:31
Hall Bath 1 | Vanity | Replace | 8:37
Hall Bath 1 | Tub | Reglaze; keep fiberglass tub | 8:44
Hall Bath 2 | Tub | Reglaze | 11:12
Hall Bath 2 | Vanity | Replace | 11:21
All Baths | Wall Surfaces | Keep existing wall finishes (paneling) | Clarified
All Baths | Flooring | Keep existing hard surface | Clarified
🟦 BEDROOMS
Location | Item | Description | Timestamp
Bedrooms | Ceiling | Remove popcorn ceiling | 8:53–9:09
Bedrooms | Doors | Replace only damaged ones; paint rest | 9:22
Bedrooms | Flooring | Install carpet | Flooring Directive
🟦 KITCHEN
Location | Item | Description | Timestamp
Kitchen Ceiling | Drop Ceiling | Remove entire drop ceiling | 10:23
Kitchen/Bar Wall | Wall Removal | Remove wall between kitchen and bar | 10:29
Kitchen | Upper Soffit/Structure | Remove overhead structures | 10:46
Kitchen | Cabinets | Replace full kitchen cabinets (implied by “redo kitchen”) | 10:52
Kitchen | Layout | Keep general configuration same except wall removal | 12:11
Kitchen | Flooring | Install laminate ($1.49) | Flooring Directive
🟦 LAUNDRY
Location | Item | Description | Timestamp
Laundry | Cabinets | Keep and paint | 11:05
Laundry | Flooring | Laminate | Flooring Directive
🟦 GENERAL INTERIOR
Location | Item | Description | Timestamp
Entire House | Popcorn Removal | Remove popcorn everywhere except garage | 6:36
Doors/Hardware | Door knobs | Replace all | multiple
Baseboards | Trim | Keep baseboards; repaint | 8:16
Windows | Windows | Keep; clean thoroughly | 13:31
HVAC | System | Evaluate; verify function | 9:38
Entire House | Paint | Full interior repaint | all
Trash | Interior Trash | Remove trash including large safe | 16:24

## Sheet5
Type | Date | Num | Name | Memo | Amount | Balance
150 · Properties
150.019 · 15620 Ramona Ave
Credit Card Charge | 2025-09-27 |  | BURNS SEPTIC SEWER |  | 540.75 | 540.75 | Rehab | Other
General Journal | 2025-10-02 | 247 |  | 15620 Ramona EMD | 10000 | 10540.75 | Acquisition
Check | 2025-10-30 | ACH | US Assure |  | 2003 | 12543.75 | Holding
Check | 2025-10-30 | ACH | Neptune Flood |  | 3758.38 | 16302.13 | Holding
Check | 2025-11-07 | WIRE | Autumn Skye Escrow Services |  | 5230.45 | 21532.58 | Acquisition
General Journal | 2025-11-07 | 252 |  | 15620 Ramona | 308000 | 329532.58 | Acquisition
Check | 2025-11-17 | ZELLE | Eagle Management |  | 500 | 330032.58 | Acquisition
Credit Card Charge | 2025-11-25 | 292 | DUMPSTER RENTAL ENTERP |  | 820.16 | 330852.74 | Rehab | Other
Credit Card Charge | 2025-11-25 | 315 | THE HOME DEPOT #6834 |  | 894.88 | 331747.62 | Rehab | Materials
Credit Card Charge | 2025-11-26 | 314 | THE HOME DEPOT #6834 |  | 1354.8 | 333102.42 | Rehab | Materials
General Journal | 2025-11-28 | 248 |  | Anguiano Armenta | 1000 | 334102.42 | Rehab | Labor
Credit Card Charge | 2025-11-28 | 313 | THE HOME DEPOT #6834 |  | 781.09 | 334883.51 | Rehab | Materials
Credit Card Credit | 2025-11-29 |  | THE HOME DEPOT #1844 |  | -146.37 | 334737.14 | Rehab | Materials
Credit Card Charge | 2025-11-29 | 310 | THE HOME DEPOT #1844 |  | 583.89 | 335321.03 | Rehab | Materials
Check | 2025-12-01 | Wire | Anguiano Armenta Construction |  | 5000 | 340321.03 | Rehab | Labor
Credit Card Charge | 2025-12-01 | 291 | DUMPSTER RENTAL ENTERP |  | 882.31 | 341203.34 | Rehab | Other
Credit Card Charge | 2025-12-01 | 309 | THE HOME DEPOT #1844 |  | 191.93 | 341395.27 | Rehab | Materials
Credit Card Charge | 2025-12-02 | 308 | THE HOME DEPOT #1844 |  | 533.08 | 341928.35 | Rehab | Materials
Credit Card Charge | 2025-12-03 | 305 | THE HOME DEPOT #1844 |  | 1 | 341929.35 | Rehab | Materials
Credit Card Charge | 2025-12-03 | 306 | THE HOME DEPOT #1844 |  | 175.52 | 342104.87 | Rehab | Materials
Credit Card Charge | 2025-12-03 | 307 | THE HOME DEPOT #1844 |  | 242.79 | 342347.66 | Rehab | Materials
Credit Card Charge | 2025-12-04 | 304 | THE HOME DEPOT #1844 |  | 910.13 | 343257.79 | Rehab | Materials
Check | 2025-12-05 | Wire | Anguiano Armenta Construction |  | 6000 | 349257.79 | Rehab | Labor
Check | 2025-12-05 | Zelle | Ovier Calva Bautista |  | 2000 | 351257.79 | Rehab | Other
Credit Card Charge | 2025-12-05 | 302 | THE HOME DEPOT #1844 |  | 61.25 | 351319.04 | Rehab | Materials
Credit Card Charge | 2025-12-05 | 303 | THE HOME DEPOT #1844 |  | 86.98 | 351406.02 | Rehab | Materials
Deposit | 2025-12-08 |  | Autumn Skye Escrow Services | Escrow Refund | -97.5 | 351308.52 | Acquisition
Deposit | 2025-12-08 |  | Kelvin | Draw Fee | 179 | 351487.52 | Holding
Credit Card Charge | 2025-12-08 | 295 | SHERWIN-WILLIAMS701614 |  | 150.61 | 351638.13 | Rehab | Materials
Credit Card Charge | 2025-12-09 | 301 | THE HOME DEPOT #1844 |  | 220.44 | 351858.57 | Rehab | Materials
Credit Card Charge | 2025-12-10 | 288 | DUMPSTER RENTAL ENTERP |  | 82.4 | 351940.97 | Rehab | Other
Credit Card Charge | 2025-12-10 | 289 | DUMPSTER RENTAL ENTERP |  | 457.85 | 352398.82 | Rehab | Other
Credit Card Charge | 2025-12-10 | 290 | DUMPSTER RENTAL ENTERP |  | 82.4 | 352481.22 | Rehab | Other
Check | 2025-12-11 | Zelle | Crecencio Chavez | Flooring | 2903.18 | 355384.4 | Rehab | Materials
Credit Card Charge | 2025-12-11 | 287 | DUMPSTER RENTAL ENTERP |  | 82.4 | 355466.8 | Rehab | Other
Check | 2025-12-12 |  |  |  | 12.5 | 355479.3 | Rehab | Labor
Check | 2025-12-12 |  | Anguiano Armenta Construction |  | 6000 | 361479.3 | Rehab | Labor
Credit Card Charge | 2025-12-12 | 286 | DUMPSTER RENTAL ENTERP |  | 82.4 | 361561.7 | Rehab | Other
Credit Card Charge | 2025-12-12 | 300 | THE HOME DEPOT #1844 |  | 885.93 | 362447.63 | Rehab | Materials
Credit Card Charge | 2025-12-13 | 285 | DUMPSTER RENTAL ENTERP |  | 82.4 | 362530.03 | Rehab | Other
Check | 2025-12-14 | 1025 | Ovier Calva Bautista |  | 1250 | 363780.03 | Rehab | Other
Credit Card Charge | 2025-12-14 | 284 | DUMPSTER RENTAL ENTERP |  | 82.4 | 363862.43 | Rehab | Other
Credit Card Charge | 2025-12-15 | 283 | DUMPSTER RENTAL ENTERP |  | 82.4 | 363944.83 | Rehab | Other
Credit Card Charge | 2025-12-15 | 294 | HM FLOORING GROUP |  | 922.76 | 364867.59 | Rehab | Materials
Credit Card Charge | 2025-12-15 | 299 | THE HOME DEPOT #1844 |  | 929.69 | 365797.28 | Rehab | Materials
Credit Card Charge | 2025-12-16 | 282 | DUMPSTER RENTAL ENTERP |  | 82.4 | 365879.68 | Rehab | Other
Credit Card Charge | 2025-12-16 | 298 | THE HOME DEPOT #1844 |  | 385.3 | 366264.98 | Rehab | Materials
Credit Card Charge | 2025-12-16 | 319 | USA Zhongheng Corp |  | 3506.53 | 369771.51 | Rehab | Materials
Credit Card Charge | 2025-12-17 | 281 | DUMPSTER RENTAL ENTERP |  | 82.4 | 369853.91 | Rehab | Other
Credit Card Charge | 2025-12-17 | 311 | THE HOME DEPOT #6834 |  | 164.9 | 370018.81 | Rehab | Materials
Credit Card Charge | 2025-12-17 | 312 | THE HOME DEPOT #6834 |  | 1465.66 | 371484.47 | Rehab | Materials
Credit Card Charge | 2025-12-18 | 280 | DUMPSTER RENTAL ENTERP |  | 82.4 | 371566.87 | Rehab | Other
Check | 2025-12-19 |  |  | Wire Fee | 25 | 371591.87 | Rehab | Labor
Check | 2025-12-19 |  | Anguiano Armenta Construction |  | 6000 | 377591.87 | Rehab | Labor
Deposit | 2025-12-19 |  | Kiavi | Draw Fee | 179 | 377770.87 | Holding
Credit Card Charge | 2025-12-19 | 278 | DUMPSTER RENTAL ENTERP |  | 38 | 377808.87 | Rehab | Other
Credit Card Charge | 2025-12-19 | 279 | DUMPSTER RENTAL ENTERP |  | 82.4 | 377891.27 | Rehab | Other
Credit Card Charge | 2025-12-19 | 297 | THE HOME DEPOT #1844 |  | 2402.16 | 380293.43 | Rehab | Materials
Credit Card Charge | 2025-12-20 | 277 | DUMPSTER RENTAL ENTERP |  | 82.4 | 380375.83 | Rehab | Other
Credit Card Charge | 2025-12-20 | 296 | THE HOME DEPOT #1844 |  | 448.37 | 380824.2 | Rehab | Materials
Credit Card Charge | 2025-12-21 | 276 | DUMPSTER RENTAL ENTERP |  | 82.4 | 380906.6 | Rehab | Other
Credit Card Charge | 2025-12-22 | 275 | DUMPSTER RENTAL ENTERP |  | 82.4 | 380989 | Rehab | Other
Credit Card Charge | 2025-12-23 | 316 | THE HOME DEPOT #6834 |  | 67.31 | 381056.31 | Rehab | Materials
Credit Card Charge | 2025-12-23 | 317 | THE HOME DEPOT #6834 |  | 582.61 | 381638.92 | Rehab | Materials
Credit Card Charge | 2025-12-23 | 318 | THE HOME DEPOT #6834 |  | 382.54 | 382021.46 | Rehab | Materials
Credit Card Credit | 2025-12-26 |  | Home Depot |  | -169.46 | 381852 | Rehab | Materials
Credit Card Charge | 2025-12-29 |  | SO CALIFORNIA EDISON |  | 46.06 | 381898.06 | Holding
Check | 2025-12-29 | Zelle | Alfonso Cano |  | 3000 | 384898.06 | Rehab | Other
Check | 2025-12-29 |  | Anguiano Armenta Construction |  | 4500 | 389398.06 | Rehab | Labor
Check | 2025-12-29 |  |  | Wire Fee | 12.5 | 389410.56 | Rehab | Labor
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 389328.16 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 389245.76 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 389163.36 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 389080.96 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -38 | 389042.96 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388960.56 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388878.16 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388795.76 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388713.36 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388630.96 | Rehab | Other
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 388548.56 | Rehab | Other
Credit Card Charge | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | 38 | 388586.56 | Rehab | Other
Credit Card Charge | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | 819.84 | 389406.4 | Rehab | Other
Check | 2025-12-30 | Zelle | Window Guy |  | 900 | 390306.4 | Rehab | Other
Credit Card Charge | 2025-12-31 |  | Home Depot |  | 82.72 | 390389.12 | Rehab | Materials
Check | 2026-01-02 |  | Kiavi |  | 2902.2 | 393291.32 | Holding
Deposit | 2026-01-06 |  | Kiavi | Draw Fee | 179 | 393470.32 | Holding
Check | 2026-01-06 | ACH | The Elite Group |  | 499 | 393969.32 | Rehab | Other
Credit Card Charge | 2026-01-08 |  | SQ *CHRISTIAN ARIAS |  | 200 | 394169.32 | Holding
Check | 2026-01-09 | WIRE | Anguiano Armenta Construction | Labor | 1600 | 395769.32 | Rehab | Labor
Check | 2026-01-09 | WIRE | Anguiano Armenta Construction | Materials | 518.44 | 396287.76 | Rehab | Materials
Check | 2026-01-12 | Zelle | Anguiano Armenta Construction |  | 900 | 397187.76 | Rehab | Other
Credit Card Charge | 2026-01-19 |  | Home Depot |  | 904.42 | 398092.18 | Rehab | Materials
Check | 2026-01-21 | Zelle | Jose Cazares | Windows | 925 | 399017.18 | Rehab | Other
Credit Card Charge | 2026-01-26 |  | SO CALIFORNIA EDISON |  | 42.61 | 399059.79 | Holding
Credit Card Charge | 2026-01-28 |  | Home Depot |  | 41.5 | 399101.29 | Rehab | Materials
Check | 2026-02-02 | ACH | Kiavi |  | 3197.77 | 402299.06 | Holding
Credit Card Charge | 2026-02-18 |  | SO CALIFORNIA EDISON |  | 36.95 | 402336.01 | Holding
Check | 2026-02-20 | 1027 | Alberto Banuelos |  | 250 | 402586.01 | Rehab | Other
Credit Card Charge | 2026-02-21 |  | Home Depot |  | 781.67 | 403367.68 | Rehab | Materials
Check | 2026-03-02 | ACH | Kiavi |  | 3230.79 | 406598.47 | Holding
Credit Card Charge | 2026-03-09 |  | Home Depot |  | 170.37 | 406768.84 | Rehab | Materials
Credit Card Charge | 2026-03-19 |  | SCE |  | 27.3 | 406796.14 | Holding
Credit Card Charge | 2026-03-27 |  | LU CA /EZ-PAY |  | 500 | 407296.14 | Holding
Credit Card Charge | 2026-03-27 |  | LU CA /EZ-PAY |  | 129.99 | 407426.13 | Holding
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 175.04 | 407601.17 | Rehab | Materials
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 160.97 | 407762.14 | Rehab | Materials
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 43.46 | 407805.6 | Rehab | Materials
Check | 2026-03-30 | 1029 | Alberto Banuelos |  | 600 | 408405.6 | Rehab | Other
Check | 2026-04-01 | ACH | Kiavi |  | 3230.79 | 411636.39 | Holding
Check | 2026-04-15 | ZELLE | Anguiano Armenta Construction |  | 150 | 411786.39 | Rehab | Other
Check | 2026-04-20 | 1030 | Jose Rodriguez |  | 5680 | 417466.39 | Rehab | Other
Check | 2026-05-01 | ACH | Kiavi |  | 3230.79 | 420697.18 | Holding
Deposit | 2026-05-06 |  | Diamond Quality Escrow | Escrow | -3000 | 417697.18 | Holding
Check | 2026-06-01 | ACH | Kiavi |  | 3230.79 | 420927.97 | Holding
Credit Card Charge | 2026-06-01 |  | Southwest Gas |  | 139.25 | 421067.22 | Holding
Credit Card Charge | 2026-06-03 |  | APPLE VALLEY FPD CA |  | 181 | 421248.22 | Rehab | Other
Total 150.019 · 15620 Ramona Ave |  |  |  |  | 421248.22 | 421248.22
Total 150 · Properties |  |  |  |  | 421248.22 | 421248.22
TOTAL |  |  |  |  | 421248.22 | 421248.22

## Sheet6
Type | Date | Num | Name | Memo | Amount | Balance | 12% | Date Interest To | 2026-06-19
150.019 · 15620 Ramona Ave | [6 empty] | Days Outstanding | Interest
Credit Card Charge | 2025-09-27 |  | BURNS SEPTIC SEWER |  | 540.75 | 540.75 | 263 | 47.41
General Journal | 2025-10-02 | 247 |  | 15620 Ramona EMD | 10000 | 10540.75 | 258 | 860
Check | 2025-10-30 | ACH | US Assure |  | 2003 | 12543.75 | 230 | 153.56
Check | 2025-10-30 | ACH | Neptune Flood |  | 3758.38 | 16302.13 | 230 | 288.14
Check | 2025-11-07 | WIRE | Autumn Skye Escrow Services |  | 5230.45 | 21532.58 | 223 | 388.8
Check | 2025-11-17 | ZELLE | Eagle Management |  | 500 | 22032.58 | 213 | 35.5
Credit Card Charge | 2025-11-25 | 292 | DUMPSTER RENTAL ENTERP |  | 820.16 | 22852.74 | 205 | 56.04
Credit Card Charge | 2025-11-25 | 315 | THE HOME DEPOT #6834 |  | 894.88 | 23747.62 | 205 | 61.15
Credit Card Charge | 2025-11-26 | 314 | THE HOME DEPOT #6834 |  | 1354.8 | 25102.42 | 204 | 92.13
General Journal | 2025-11-28 | 248 |  | Anguiano Armenta | 1000 | 26102.42 | 202 | 67.33
Credit Card Charge | 2025-11-28 | 313 | THE HOME DEPOT #6834 |  | 781.09 | 26883.51 | 202 | 52.59
Credit Card Credit | 2025-11-29 |  | THE HOME DEPOT #1844 |  | -146.37 | 26737.14 | 201 | -9.81
Credit Card Charge | 2025-11-29 | 310 | THE HOME DEPOT #1844 |  | 583.89 | 27321.03 | 201 | 39.12
Check | 2025-12-01 | Wire | Anguiano Armenta Construction |  | 5000 | 32321.03 | 199 | 331.67
Credit Card Charge | 2025-12-01 | 291 | DUMPSTER RENTAL ENTERP |  | 882.31 | 33203.34 | 199 | 58.53
Credit Card Charge | 2025-12-01 | 309 | THE HOME DEPOT #1844 |  | 191.93 | 33395.27 | 199 | 12.73
Credit Card Charge | 2025-12-02 | 308 | THE HOME DEPOT #1844 |  | 533.08 | 33928.35 | 198 | 35.18
Credit Card Charge | 2025-12-03 | 305 | THE HOME DEPOT #1844 |  | 1 | 33929.35 | 197 | 0.07
Credit Card Charge | 2025-12-03 | 306 | THE HOME DEPOT #1844 |  | 175.52 | 34104.87 | 197 | 11.53
Credit Card Charge | 2025-12-03 | 307 | THE HOME DEPOT #1844 |  | 242.79 | 34347.66 | 197 | 15.94
Credit Card Charge | 2025-12-04 | 304 | THE HOME DEPOT #1844 |  | 910.13 | 35257.79 | 196 | 59.46
Check | 2025-12-05 | Wire | Anguiano Armenta Construction |  | 6000 | 41257.79 | 195 | 390
Check | 2025-12-05 | Zelle | Ovier Calva Bautista |  | 2000 | 43257.79 | 195 | 130
Credit Card Charge | 2025-12-05 | 302 | THE HOME DEPOT #1844 |  | 61.25 | 43319.04 | 195 | 3.98
Credit Card Charge | 2025-12-05 | 303 | THE HOME DEPOT #1844 |  | 86.98 | 43406.02 | 195 | 5.65
Deposit | 2025-12-08 |  | Autumn Skye Escrow Services | Escrow Refund | -97.5 | 43308.52 | 192 | -6.24
Deposit | 2025-12-08 |  | Kiavi |  | -25000 | 18308.52 | 192 | -1600
Deposit | 2025-12-08 |  | Kiavi | Draw Fee | 179 | 18487.52 | 192 | 11.46
Credit Card Charge | 2025-12-08 | 295 | SHERWIN-WILLIAMS701614 |  | 150.61 | 18638.13 | 192 | 9.64
Credit Card Charge | 2025-12-09 | 301 | THE HOME DEPOT #1844 |  | 220.44 | 18858.57 | 191 | 14.03
Credit Card Charge | 2025-12-10 | 288 | DUMPSTER RENTAL ENTERP |  | 82.4 | 18940.97 | 190 | 5.22
Credit Card Charge | 2025-12-10 | 289 | DUMPSTER RENTAL ENTERP |  | 457.85 | 19398.82 | 190 | 29
Credit Card Charge | 2025-12-10 | 290 | DUMPSTER RENTAL ENTERP |  | 82.4 | 19481.22 | 190 | 5.22
Check | 2025-12-11 | Zelle | Crecencio Chavez | Flooring | 2903.18 | 22384.4 | 189 | 182.9
Credit Card Charge | 2025-12-11 | 287 | DUMPSTER RENTAL ENTERP |  | 82.4 | 22466.8 | 189 | 5.19
Check | 2025-12-12 |  |  |  | 12.5 | 22479.3 | 188 | 0.78
Check | 2025-12-12 |  | Anguiano Armenta Construction |  | 6000 | 28479.3 | 188 | 376
Credit Card Charge | 2025-12-12 | 286 | DUMPSTER RENTAL ENTERP |  | 82.4 | 28561.7 | 188 | 5.16
Credit Card Charge | 2025-12-12 | 300 | THE HOME DEPOT #1844 |  | 885.93 | 29447.63 | 188 | 55.52
Credit Card Charge | 2025-12-13 | 285 | DUMPSTER RENTAL ENTERP |  | 82.4 | 29530.03 | 187 | 5.14
Check | 2025-12-14 | 1025 | Ovier Calva Bautista |  | 1250 | 30780.03 | 186 | 77.5
Credit Card Charge | 2025-12-14 | 284 | DUMPSTER RENTAL ENTERP |  | 82.4 | 30862.43 | 186 | 5.11
Credit Card Charge | 2025-12-15 | 283 | DUMPSTER RENTAL ENTERP |  | 82.4 | 30944.83 | 185 | 5.08
Credit Card Charge | 2025-12-15 | 294 | HM FLOORING GROUP |  | 922.76 | 31867.59 | 185 | 56.9
Credit Card Charge | 2025-12-15 | 299 | THE HOME DEPOT #1844 |  | 929.69 | 32797.28 | 185 | 57.33
Credit Card Charge | 2025-12-16 | 282 | DUMPSTER RENTAL ENTERP |  | 82.4 | 32879.68 | 184 | 5.05
Credit Card Charge | 2025-12-16 | 298 | THE HOME DEPOT #1844 |  | 385.3 | 33264.98 | 184 | 23.63
Credit Card Charge | 2025-12-16 | 319 | USA Zhongheng Corp |  | 3506.53 | 36771.51 | 184 | 215.07
Credit Card Charge | 2025-12-17 | 281 | DUMPSTER RENTAL ENTERP |  | 82.4 | 36853.91 | 183 | 5.03
Credit Card Charge | 2025-12-17 | 311 | THE HOME DEPOT #6834 |  | 164.9 | 37018.81 | 183 | 10.06
Credit Card Charge | 2025-12-17 | 312 | THE HOME DEPOT #6834 |  | 1465.66 | 38484.47 | 183 | 89.41
Credit Card Charge | 2025-12-18 | 280 | DUMPSTER RENTAL ENTERP |  | 82.4 | 38566.87 | 182 | 5
Check | 2025-12-19 |  |  | Wire Fee | 25 | 38591.87 | 181 | 1.51
Check | 2025-12-19 |  | Anguiano Armenta Construction |  | 6000 | 44591.87 | 181 | 362
Deposit | 2025-12-19 |  | Kiavi |  | -15250 | 29341.87 | 181 | -920.08
Deposit | 2025-12-19 |  | Kiavi | Draw Fee | 179 | 29520.87 | 181 | 10.8
Credit Card Charge | 2025-12-19 | 278 | DUMPSTER RENTAL ENTERP |  | 38 | 29558.87 | 181 | 2.29
Credit Card Charge | 2025-12-19 | 279 | DUMPSTER RENTAL ENTERP |  | 82.4 | 29641.27 | 181 | 4.97
Credit Card Charge | 2025-12-19 | 297 | THE HOME DEPOT #1844 |  | 2402.16 | 32043.43 | 181 | 144.93
Credit Card Charge | 2025-12-20 | 277 | DUMPSTER RENTAL ENTERP |  | 82.4 | 32125.83 | 180 | 4.94
Credit Card Charge | 2025-12-20 | 296 | THE HOME DEPOT #1844 |  | 448.37 | 32574.2 | 180 | 26.9
Credit Card Charge | 2025-12-21 | 276 | DUMPSTER RENTAL ENTERP |  | 82.4 | 32656.6 | 179 | 4.92
Credit Card Charge | 2025-12-22 | 275 | DUMPSTER RENTAL ENTERP |  | 82.4 | 32739 | 178 | 4.89
Credit Card Charge | 2025-12-23 | 316 | THE HOME DEPOT #6834 |  | 67.31 | 32806.31 | 177 | 3.97
Credit Card Charge | 2025-12-23 | 317 | THE HOME DEPOT #6834 |  | 582.61 | 33388.92 | 177 | 34.37
Credit Card Charge | 2025-12-23 | 318 | THE HOME DEPOT #6834 |  | 382.54 | 33771.46 | 177 | 22.57
Credit Card Credit | 2025-12-26 |  | Home Depot |  | -169.46 | 33602 | 174 | -9.83
Credit Card Charge | 2025-12-29 |  | SO CALIFORNIA EDISON |  | 46.06 | 33648.06 | 171 | 2.63
Check | 2025-12-29 | Zelle | Alfonso Cano |  | 3000 | 36648.06 | 171 | 171
Check | 2025-12-29 |  | Anguiano Armenta Construction |  | 4500 | 41148.06 | 171 | 256.5
Check | 2025-12-29 |  |  | Wire Fee | 12.5 | 41160.56 | 171 | 0.71
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 41078.16 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40995.76 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40913.36 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40830.96 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -38 | 40792.96 | 170 | -2.15
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40710.56 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40628.16 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40545.76 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40463.36 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40380.96 | 170 | -4.67
Credit Card Credit | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | -82.4 | 40298.56 | 170 | -4.67
Credit Card Charge | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | 38 | 40336.56 | 170 | 2.15
Credit Card Charge | 2025-12-30 |  | DUMPSTER RENTAL ENTERP |  | 819.84 | 41156.4 | 170 | 46.46
Check | 2025-12-30 | Zelle | Window Guy |  | 900 | 42056.4 | 170 | 51
Credit Card Charge | 2025-12-31 |  | Home Depot |  | 82.72 | 42139.12 | 170 | 4.69
Check | 2026-01-02 |  | Kiavi |  | 2902.2 | 45041.32 | 168 | 162.52
Deposit | 2026-01-06 |  | Kiavi |  | -22750 | 22291.32 | 164 | -1243.67
Deposit | 2026-01-06 |  | Kiavi | Draw Fee | 179 | 22470.32 | 164 | 9.79
Check | 2026-01-06 | ACH | The Elite Group |  | 499 | 22969.32 | 164 | 27.28
Credit Card Charge | 2026-01-08 |  | SQ *CHRISTIAN ARIAS |  | 200 | 23169.32 | 162 | 10.8
Check | 2026-01-09 | WIRE | Anguiano Armenta Construction | Labor | 1600 | 24769.32 | 161 | 85.87
Check | 2026-01-09 | WIRE | Anguiano Armenta Construction | Materials | 518.44 | 25287.76 | 161 | 27.82
Check | 2026-01-12 | Zelle | Anguiano Armenta Construction |  | 900 | 26187.76 | 158 | 47.4
Credit Card Charge | 2026-01-19 |  | Home Depot |  | 904.42 | 27092.18 | 151 | 45.52
Check | 2026-01-21 | Zelle | Jose Cazares | Windows | 925 | 28017.18 | 149 | 45.94
Credit Card Charge | 2026-01-26 |  | SO CALIFORNIA EDISON |  | 42.61 | 28059.79 | 144 | 2.05
Credit Card Charge | 2026-01-28 |  | Home Depot |  | 41.5 | 28101.29 | 142 | 1.96
Check | 2026-02-02 | ACH | Kiavi |  | 3197.77 | 31299.06 | 138 | 147.1
Credit Card Charge | 2026-02-18 |  | SO CALIFORNIA EDISON |  | 36.95 | 31336.01 | 122 | 1.5
Check | 2026-02-20 | 1027 | Alberto Banuelos |  | 250 | 31586.01 | 120 | 10
Credit Card Charge | 2026-02-21 |  | Home Depot |  | 781.67 | 32367.68 | 119 | 31.01
Check | 2026-03-02 | ACH | Kiavi |  | 3230.79 | 35598.47 | 108 | 116.31
Credit Card Charge | 2026-03-09 |  | Home Depot |  | 170.37 | 35768.84 | 101 | 5.74
Credit Card Charge | 2026-03-19 |  | SCE |  | 27.3 | 35796.14 | 91 | 0.83
Credit Card Charge | 2026-03-27 |  | LU CA /EZ-PAY |  | 500 | 36296.14 | 83 | 13.83
Credit Card Charge | 2026-03-27 |  | LU CA /EZ-PAY |  | 129.99 | 36426.13 | 83 | 3.6
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 175.04 | 36601.17 | 82 | 4.78
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 160.97 | 36762.14 | 82 | 4.4
Credit Card Charge | 2026-03-28 |  | Home Depot |  | 43.46 | 36805.6 | 82 | 1.19
Check | 2026-03-30 | 1029 | Alberto Banuelos |  | 600 | 37405.6 | 80 | 16
Check | 2026-04-01 | ACH | Kiavi |  | 3230.79 | 40636.39 | 79 | 85.08
Check | 2026-04-15 | ZELLE | Anguiano Armenta Construction |  | 150 | 40786.39 | 65 | 3.25
Check | 2026-04-20 | 1030 | Jose Rodriguez |  | 5680 | 46466.39 | 60 | 113.6
Check | 2026-05-01 | ACH | Kiavi |  | 3230.79 | 49697.18 | 49 | 52.77
Deposit | 2026-05-06 |  | Diamond Quality Escrow | Escrow | -3000 | 46697.18 | 44 | -44
Check | 2026-06-01 | ACH | Kiavi |  | 3230.79 | 49927.97 | 19 | 20.46
Credit Card Charge | 2026-06-01 |  | Southwest Gas |  | 139.25 | 50067.22 | 19 | 0.88
Credit Card Charge | 2026-06-03 |  | APPLE VALLEY FPD CA |  | 181 | 50248.22 | 17 | 1.03
Total 150.019 · 15620 Ramona Ave |  |  |  |  | 50248.22 | 50248.22 |  | 2838.97
Total 150 · Properties |  |  |  |  | 50248.22 | 50248.22
TOTAL |  |  |  |  | 50248.22 | 50248.22